## MCM
project:
calculator:
date:
WBS id | predecessor | task; format.. location - sensor - function location - name | requirement level (MoSCoW) | developer | Risc | duration (plan) min | duration (do) min | reflection (check) | transfer (act) | IPC | completed
[6 empty] | 630 | 90
10.5
each task contains model/view/API
1 |  | RS - compass - roll | M
2 |  | RS - compass - pitch | M
3 |  | RS - compass - bearing | M
4 |  | RS - acceleration | M
5 |  | RS - temperature | M
6 |  | RS - Barometer | M
7 |  | TPS - value indicator | M
8 |  | TPS - unit selector - pulldown (Bar, Mpa, psi) | M
9 |  | LPM -RS on launch pad detector | M
10 |  | LPM - down force at launch | M
11 |  | LPM - GPS module for future web interface | S
12 |  | LPM - PRV indicator (piezo element) | M
13 |  | GCM - Set Altitude Button | M
14 |  | GCM - Set Altitude Value | M
15 |  | GCM - Launch Button | M
16 |  | GCM - Count Down Time | M
17 |  | GCM - Launch indicator | M
18 |  | GCM - Launch Override | M
19 |  | LPM - RS launch pad detector override | M
20 |  | RS - battery level | M
21 |  | RS - activate beacon LED | S
22 |  | GCM - launch abort button | M
23 |  | API modelling | M |  |  | 90
24 |  | Total system simulator | S |  |  | 120
25 |  | Stub | M |  | functions not the same as the real world | 120
26 |  | MCM - TX to GCM comm code and view (copy from earlier project) | M |  |  | 90
27 |  | MCM - RX from GCM comm code and view (copy from earlier project) | M |  |  | 90
28 |  | MCM - basic design set up | M |  |  | 60
29 |  | MCM - version control in GIT | M |  |  | 30 | 90 | problem with correct directory | handling now documented
30 |  | MCM - serial setup with Arduin/ESP32 (copy from earlier project) | M |  |  | 30
31 |  | MCM - debug window (copy from eralier project) | M
32
33
34
|  | totaal |  |  |  | 630 | 90

## Abbreviations
RS | Rocket System
TPS | Tank Pressure Sensor
LPM | Launch Pad Module
PRV | Pressure Release Valve

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma